## Tabelle1
Feature Number | Feature Name | User Story Number | User Story Name | Story Points | Sprint | Owner | Scrum Team | Dependency | Comments
149032 | [11.x] RevTrac Octane Integration (Stretch) | 182038 | [11x] Gathering the requirements for Octane Rev Trac interface | 1 |  | Izabela von Mach | SCOP
199004 | [11.x] RevTrac SNOW connection | 255329 | [11.1] Request firewall change (open port from new RevTrac VM to SNOW Dev and UAT Linux mid-servers) | 1 | 1 | Girish Bandi | SCOP
199004 | asda das asd sa | 192009 | [11.4] Configure SNOW DEV and UAT Linux mid-servers for RevTrac integration | 2 | 4 | Florestan Koenigs | SCOP
199004 | [11.x] RevTrac SNOW connection | 255353 | [11.5] Order new Windows mid-servers with SMO team | 1 | 5 | Jonathan Charette | SCOP
199004 | [11.x] RevTrac SNOW connection | 256390 | [11.5] Handover Windows mid-servers to SNOW team | 1 | 5 | Florestan Koenigs | SCOP
199004 | [11.x] RevTrac SNOW connection | 255355 | [11.5] Handover and documentation of mid-server configuration for RevTrac to SNOW team | 2 | 5 | Florestan Koenigs | SCOP
199004 | [11.x] RevTrac SNOW connection | 256391 | [11.5] Configure SNOW PROD mid-server for RevTrac integration | 2 | 5 | Florestan Koenigs | SCOP
199004 | [11.x] RevTrac SNOW connection | 255349 | [11.4] Test connection of new RevTrac VM to SNOW Cloud DEV and UAT instances | 1 | 4 | Florestan Koenigs | SCOP
219007 | [11.x] Tosca Regression Pack Activation | 255357 | [11.4] Automate the Tosca reports | 4 | 4 | Renan Gaspar | SCOP
221002 | [11.x] RevTrac improvement | 256358 | [11.1] Preparation of new RevTrac VM server | 2 | 1 | Florestan Koenigs | SCOP
221002 | [11.x] RevTrac improvement | 203048 | [11.2] Core installation on new Rev Trac VM | 3 | 2 | Florestan Koenigs | SCOP
221002 | [11.x] RevTrac improvement | 256380 | [11.2] DB backup of existing RevTrac VM | 1 | 2 | Florestan Koenigs | SCOP
221002 | [11.x] RevTrac improvement | 256381 | [11.2] Install upgrade package on new RevTrac VM | 2 | 2 | Florestan Koenigs | SCOP
221002 | [11.x] RevTrac improvement | 256384 | [11.3] Import of DB backup to new RevTrac VM | 1 | 3 | Florestan Koenigs | SCOP
221002 | [11.x] RevTrac improvement | 255344 | [11.3] Configuration of new RevTrac VM | 5 | 3 | Girish Bandi | SCOP
221002 | [11.x] RevTrac improvement | 256359 | [11.1] Request certificates for new RevTrac VM server | 1 | 1 | Girish Bandi | SCOP
221002 | [11.x] RevTrac improvement | 255345 | [11.3] Install certificates for new RevTrac VM server | 3 | 3 | Girish Bandi | SCOP
256103 | [11.x] RevTrac Tosca Integration improvement | 256322 | [11.1] Create Tosca XML Files to RevTrac | 1 | 1 | Renan Gaspar | SCOP
256103 | [11.x] RevTrac Tosca Integration improvement | 255299 | [11.2] Customize new RevTrac field for Tosca package | 1 | 2 | Izabela von Mach | SCOP
256103 | [11.x] RevTrac Tosca Integration improvement | 256324 | [11.3] Integrate new RevTrac field for Tosca in the User Exit as parameter | 3 | 3 | Izabela von Mach | SCOP
221002 | [11.x] RevTrac improvement | 205053 | [11.3] Finalizing RevTrac VM Configuration | 3 | 3 | Girish Bandi | Scop
221002 | [11.x] RevTrac improvement | 203067 | [11.1] Handover RevTrac VM to Platform team | 2 | 1 | Girish Bandi | Scop
221002 | [11.x] RevTrac improvement | 205056 | [11.3] Documentation of RevTrac VM | 5 | 3 | Girish Bandi | Scop
255296 | [11x] FX reval indexes completion | 164009 | [11.2] SAP BPPO - Turn off "Invoice Summary (Japan)" according to SAP Note 1241459 | 2 | 2 | Kiran Nagaraj | Scop
255296 | [11x] FX reval indexes completion | 163020 | [11.3] SAP BPPO - Change location of ZZFAGL_FC_VAL_SKIP_FLD in AGS and AGQ | 4 | 3 | Kiran Nagaraj | Scop
255296 | [11x] FX reval indexes completion | 256360 | [11.1] Record FX runtime before index changes in AGK for I1, L1, S2, L2 | 2 | 1 | Kiran Nagaraj | Scop
255296 | [11x] FX reval indexes completion | 255342 | [11.2] Record FX runtime after index changes in AGK for I1, L1, S2, L2 | 2 | 2 | Kiran Nagaraj | Scop
255296 | [11x] FX reval indexes completion | 255330 | [11.1] Perform Index Changes on AGK for I1, L1, S2, L2 | 1 | 1 | Kiran Nagaraj | Scop
255296 | [11x] FX reval indexes completion | 255331 | [11.1] Record FX reset runtime before index changes in AGK for BKPF | 1 | 1 | Kiran Nagaraj | Scop
255296 | [11x] FX reval indexes completion | 256383 | [11.2] Record FX reset runtime after index changes in AGK for BKPF | 1 | 2 | Kiran Nagaraj | Scop
255296 | [11x] FX reval indexes completion | 255332 | [11.1] Perform Index Changes on AGK for BKPF | 1 | 1 | Kiran Nagaraj | Scop
255307 | [11.x] Performance improvements for long running jobs | 200019 | [11.2] Mapping tables for NIC interfaces - Identify the list of tables and include Data logic wherever needed1 | 2 | 2 | Kiran Nagaraj | Scop
255307 | [11.x] Performance improvements for long running jobs | 196007 | [11.4] Analyze Runtime of Brazil SAF jobs for master data extraction | 3 | 4 | Kiran Nagaraj | Scop
255307 | [11.x] Performance improvements for long running jobs | 256361 | [11.1] Evaluate potential performance improvement in FA_Reposting program | 3 | 1 | Kiran Nagaraj | Scop
256138 | [11.x] Evaluate System capacity impact for SAP ERP and SAP BW due to high granular GRID postings | 255333 | [11.1] Estimate and evaluate Data Volumen provided to SAP based on historical MIS Data | 2 | 1 | Berenice Gourmelen Schulz | SCOP
256138 | [11.x] Evaluate System capacity impact for SAP ERP and SAP BW due to high granular GRID postings | 255343 | [11.2] Validate SAP ERP and BW capacity buffer for Totals and line items tabel / Qubes | 2 | 2 | Jonathan Charette | SCOP
256138 | [11.x] Evaluate System capacity impact for SAP ERP and SAP BW due to high granular GRID postings | 256385 | [11.3] Map expected volumen against capacity buffer. Prepare recommendation system preparation on expected data volumen. | 2 | 3 | Jonathan Charette | SCOP
200002 |  | 256362 | [11.1] Import and test of SAP ERP template transports of new Release | 1 | 1 | Chandra | SCOP